## Projects
ProjectID | ReviewDate | ProjectName | LeadInterconnection | LeadHVEngineering | LeadSCADATelecom | LeadHVOM | LeadAssetMgmt | ProjectState | TOUtility | ISORTO | OTBEPAgreement | POIVoltage | POIType | Solar | Storage | PGIAGIA | COD | EPCHV | OMProvider | POIISD | POIISDStatus | EstIXCost | IXCostStatus | SolarInverters | MPT | StoragePCS | GenTieLength | ReactivePowerComp | PowerPlantCtrl | SafeHarbor | OtherAttributes | FutureExpansion | TransmissionNUs | TopGatingItem
P00 | [ MM / DD / YYYY ] | [ Project Name ] | [ Name ] | [ Name ] | [ Name ] | [ Name ] | [ Name ] | [ State ] | [ TO / Utility ] | [ ISO / RTO ] | [ Yes / No ] (add date(s) if Y) | [ ___ kV ] | [ New SS / Existing / BTM ] | [ ___ AC / ___ DC ] | [ ___ MW / ___ MWh ] | [ MM / YYYY ] | [ MM / YYYY ] | [ Contractor ] | [ Provider ] | [ MM / YYYY ] | [ On Track ] | [ $ ___ M ] | [ Within Budget ] | [ Make / Model / Qty ] | [ ___ MVA · Δ-Yg / Yg-Yg ] | [ Make / Model / Qty / Duration ] | [ Miles ] | [ Type / Size / Qty ] | [ Vendor ] | [ MPT ~ Qty / kV-MVA / FID Year ] | [ NITS, Fuel / Equip Change, etc. ] | [ Capacity / Surplus / Load IX - DC ] | [ Desc. / ISD ] | [ Top gating item ]
P01 | 07/01/2026 | Sunport Ridge Solar + Storage | K. Rivera | A. Chen | D. Okafor | M. Salinas | J. Whitfield | Texas | Oncor | ERCOT | Yes (E&P 03/2025) | 345 kV | New SS | 200 AC / 260 DC | 100 MW / 400 MWh | 08/2024 | 06/2027 | Blattner | NovaSource | 12/2026 | On Track | $14.2 M | Within Budget | Sungrow SG4400UD-MV / 46 | 230 MVA · Δ-Yg | Tesla Megapack 2XL / 100 / 4h | 3.4 miles | Cap Bank / 40 MVAr / 2 | Emerson | MPT ~ 1 / 345kV-230MVA / FID 2024 | NITS filed | Surplus IX 40 MW - DC | None | Finalize PEC scope & schedule with Oncor
P02 | 07/01/2026 | Mesa Verde Solar | S. Patel | R. Dominguez | L. Nguyen | T. Brooks | C. Ferraro | Arizona | APS | WECC (non-RTO) | No | 230 kV | Existing | 150 AC / 195 DC | 75 MW / 300 MWh | 02/2025 | 11/2027 | Rosendin | SOLV Energy | 05/2027 | At Risk | $9.8 M | Over (+$1.1 M) | GE FLEXINVERTER / 38 | 180 MVA · Yg-Yg | Fluence Gridstack / 75 / 4h | 1.2 miles | None (study pending) | Trimark | None | Fuel / equip change — N/A | Load IX 20 MW - DC | 115 kV line rebuild / 04/2027 | IX cost overrun mitigation plan with APS
P03 | 07/01/2026 | Prairie Sky Solar + Storage | E. Kowalski | H. Yamada | B. Ansari | G. Martin | N. Adeyemi | Illinois | ComEd | PJM | No | 138 kV | New SS | 300 AC / 390 DC | 150 MW / 600 MWh | 11/2025 (target) | 09/2028 | TBD (RFP Q3 2026) | TBD | 03/2028 | On Track | $22.5 M | Within Budget | TBD (shortlist: SMA / Sungrow) | 345 MVA · Δ-Yg (LOI) | TBD / 150 / 4h | 6.8 miles | STATCOM / 75 MVAr / 1 (prelim) | TBD | MPT ~ 2 / 138kV-175MVA / FID 2025 | NITS + equip change pending | Capacity +100 MW phase 2 | Desc. TBD / ISD 2028 | GIA execution with PJM / ComEd
P04 | 07/01/2026 | Cypress Bend Solar | V. Osei | P. Lindqvist | F. Cardona | I. Novak | W. Tran | Georgia | Georgia Power | SERC (non-RTO) | Yes (04/2026) | 115 kV | Existing | 120 AC / 156 DC | 50 MW / 200 MWh | 06/2024 | 12/2026 | McCarthy | Self-perform | 09/2026 | At Risk | $7.4 M | Within Budget | Power Electronics FS3430K / 30 | 150 MVA · Δ-Yg | Sungrow PowerTitan / 50 / 4h | 0.8 miles | Cap Bank / 25 MVAr / 1 | Emerson | None | — | None | Breaker upgrade / 08/2026 | Recover 8-week MPT delivery slip
P05 | 07/01/2026 | High Desert Hybrid | O. Bennett | Y. Castillo | Z. Haddad | Q. Larsen | U. Mwangi | Nevada | NV Energy | WECC (non-RTO) | Yes (E&P 01/2024) | 230 kV | New SS | 250 AC / 325 DC | 125 MW / 500 MWh | 03/2023 | 10/2026 | Mortenson | Pearce Renewables | 07/2026 | Delayed | $18.9 M | Over (+$2.4 M) | TMEIC Ninja / 52 | 280 MVA · Δ-Yg | BYD MC Cube / 125 / 4h | 4.6 miles | SVC / 60 MVAr / 1 | Trimark | MPT ~ 1 / 230kV-280MVA / FID 2022 | NITS approved | Surplus IX 30 MW - DC | None | SCADA FAT failure — retest 08/2026

## Milestones
ProjectID | Workstream | SortOrder | Label | MilestoneName | TimelinePos | RowY | Status
P00 | Commercial Analytics | 1 | C1 | Int. Basis / Curt | 5 | 5 | Not Started
P00 | Commercial Analytics | 2 | C2 | Ext. Basis / Curt | 16 | 5 | Not Started
P00 | Commercial Analytics | 3 | C3 | Study Refresh | 30 | 5 | Not Started
P00 | Commercial Analytics | 4 | C4 | 3rd Party Study | 38 | 5 | Not Started
P00 | Commercial Analytics | 5 | C5 | Ext. Re-finance | 58 | 5 | Not Started
P00 | Commercial Analytics | 6 | C6 | Outage Monitoring (Basis/Curt.) | 74 | 5 | Not Started
P00 | Interconnection | 7 | I1 | IX App / POI | 5 | 4 | Not Started
P00 | Interconnection | 8 | I2 | IX Studies | 16 | 4 | Not Started
P00 | Interconnection | 9 | I3 | GIA Execution | 30 | 4 | Not Started
P00 | Interconnection | 10 | I4 | Dyn Settings (Analysis) | 38 | 4 | Not Started
P00 | Interconnection | 11 | I5 | Dyn Settings (Testing) | 58 | 4 | Not Started
P00 | Interconnection | 12 | I6 | As-Built Mods & LC Release | 74 | 4 | Not Started
P00 | HV Engineering | 13 | 7 | MPT / HV Eqp Long-Lead | 2 | 3 | Not Started
P00 | HV Engineering | 14 | 8 | E&P / OTB | 9 | 3 | Not Started
P00 | HV Engineering | 15 | 9 | FacStudy / POI-HV Review | 28 | 3 | Not Started
P00 | HV Engineering | 16 | 10 | Reactive & PQ (Studies) | 38 | 3 | Not Started
P00 | HV Engineering | 17 | 11 | PEC | 50 | 3 | Not Started
P00 | HV Engineering | 18 | 12 | V & Q Setting (Testing) | 58 | 3 | Not Started
P00 | HV Engineering | 19 | 13 | As-Built SLD | 72 | 3 | Not Started
P00 | SCADA / Telecom | 20 | 14 | GIA Req. Rev | 30 | 2 | Not Started
P00 | SCADA / Telecom | 21 | 15 | PPA Req. Rev | 34 | 2 | Not Started
P00 | SCADA / Telecom | 22 | 16 | Vendor Sel / Long-Lead Eqp | 38 | 2 | Not Started
P00 | SCADA / Telecom | 23 | 17 | Points List Rev | 44 | 2 | Not Started
P00 | SCADA / Telecom | 24 | 18 | TELCOM / Wless (Order/Install) | 48 | 2 | Not Started
P00 | SCADA / Telecom | 25 | 19 | SCADA FAT | 54 | 2 | Not Started
P00 | SCADA / Telecom | 26 | 20 | Primary Telco | 60 | 2 | Not Started
P00 | HV O&M | 27 | 21 | Initial Design Rev. (ongoing) | 36 | 1 | Not Started
P00 | HV O&M | 28 | 22 | HV Quality Rev. (ongoing) | 42 | 1 | Not Started
P00 | HV O&M | 29 | 23 | MPT Del. / Inst. | 48 | 1 | Not Started
P00 | HV O&M | 30 | 24 | Commissioning (CMX) Testing | 54 | 1 | Not Started
P00 | HV O&M | 31 | 25 | Punch List Items | 58 | 1 | Not Started
P00 | HV O&M | 32 | 26 | CC&C | 62 | 1 | Not Started
P01 | Commercial Analytics | 1 | C1 | Int. Basis / Curt | 5 | 5 | On Track
P01 | Commercial Analytics | 2 | C2 | Ext. Basis / Curt | 16 | 5 | On Track
P01 | Commercial Analytics | 3 | C3 | Study Refresh | 30 | 5 | On Track
P01 | Commercial Analytics | 4 | C4 | 3rd Party Study | 38 | 5 | On Track
P01 | Commercial Analytics | 5 | C5 | Ext. Re-finance | 58 | 5 | Not Started
P01 | Commercial Analytics | 6 | C6 | Outage Monitoring (Basis/Curt.) | 74 | 5 | Not Started
P01 | Interconnection | 7 | I1 | IX App / POI | 5 | 4 | On Track
P01 | Interconnection | 8 | I2 | IX Studies | 16 | 4 | On Track
P01 | Interconnection | 9 | I3 | GIA Execution | 30 | 4 | On Track
P01 | Interconnection | 10 | I4 | Dyn Settings (Analysis) | 38 | 4 | On Track
P01 | Interconnection | 11 | I5 | Dyn Settings (Testing) | 58 | 4 | Not Started
P01 | Interconnection | 12 | I6 | As-Built Mods & LC Release | 74 | 4 | Not Started
P01 | HV Engineering | 13 | 7 | MPT / HV Eqp Long-Lead | 2 | 3 | On Track
P01 | HV Engineering | 14 | 8 | E&P / OTB | 9 | 3 | On Track
P01 | HV Engineering | 15 | 9 | FacStudy / POI-HV Review | 28 | 3 | On Track
P01 | HV Engineering | 16 | 10 | Reactive & PQ (Studies) | 38 | 3 | On Track
P01 | HV Engineering | 17 | 11 | PEC | 50 | 3 | At Risk
P01 | HV Engineering | 18 | 12 | V & Q Setting (Testing) | 58 | 3 | Not Started
P01 | HV Engineering | 19 | 13 | As-Built SLD | 72 | 3 | Not Started
P01 | SCADA / Telecom | 20 | 14 | GIA Req. Rev | 30 | 2 | On Track
P01 | SCADA / Telecom | 21 | 15 | PPA Req. Rev | 34 | 2 | On Track
P01 | SCADA / Telecom | 22 | 16 | Vendor Sel / Long-Lead Eqp | 38 | 2 | At Risk
P01 | SCADA / Telecom | 23 | 17 | Points List Rev | 44 | 2 | On Track
P01 | SCADA / Telecom | 24 | 18 | TELCOM / Wless (Order/Install) | 48 | 2 | Not Started
P01 | SCADA / Telecom | 25 | 19 | SCADA FAT | 54 | 2 | Not Started
P01 | SCADA / Telecom | 26 | 20 | Primary Telco | 60 | 2 | Not Started
P01 | HV O&M | 27 | 21 | Initial Design Rev. (ongoing) | 36 | 1 | On Track
P01 | HV O&M | 28 | 22 | HV Quality Rev. (ongoing) | 42 | 1 | On Track
P01 | HV O&M | 29 | 23 | MPT Del. / Inst. | 48 | 1 | Not Started
P01 | HV O&M | 30 | 24 | Commissioning (CMX) Testing | 54 | 1 | Not Started
P01 | HV O&M | 31 | 25 | Punch List Items | 58 | 1 | Not Started
P01 | HV O&M | 32 | 26 | CC&C | 62 | 1 | Not Started
P02 | Commercial Analytics | 1 | C1 | Int. Basis / Curt | 5 | 5 | On Track
P02 | Commercial Analytics | 2 | C2 | Ext. Basis / Curt | 16 | 5 | On Track
P02 | Commercial Analytics | 3 | C3 | Study Refresh | 30 | 5 | At Risk
P02 | Commercial Analytics | 4 | C4 | 3rd Party Study | 38 | 5 | Not Started
P02 | Commercial Analytics | 5 | C5 | Ext. Re-finance | 58 | 5 | Not Started
P02 | Commercial Analytics | 6 | C6 | Outage Monitoring (Basis/Curt.) | 74 | 5 | Not Started
P02 | Interconnection | 7 | I1 | IX App / POI | 5 | 4 | On Track
P02 | Interconnection | 8 | I2 | IX Studies | 16 | 4 | On Track
P02 | Interconnection | 9 | I3 | GIA Execution | 34 | 4 | At Risk
P02 | Interconnection | 10 | I4 | Dyn Settings (Analysis) | 38 | 4 | Not Started
P02 | Interconnection | 11 | I5 | Dyn Settings (Testing) | 58 | 4 | Not Started
P02 | Interconnection | 12 | I6 | As-Built Mods & LC Release | 74 | 4 | Not Started
P02 | HV Engineering | 13 | 7 | MPT / HV Eqp Long-Lead | 2 | 3 | On Track
P02 | HV Engineering | 14 | 8 | E&P / OTB | 9 | 3 | On Track
P02 | HV Engineering | 15 | 9 | FacStudy / POI-HV Review | 28 | 3 | On Track
P02 | HV Engineering | 16 | 10 | Reactive & PQ (Studies) | 38 | 3 | Not Started
P02 | HV Engineering | 17 | 11 | PEC | 50 | 3 | Not Started
P02 | HV Engineering | 18 | 12 | V & Q Setting (Testing) | 58 | 3 | Not Started
P02 | HV Engineering | 19 | 13 | As-Built SLD | 72 | 3 | Not Started
P02 | SCADA / Telecom | 20 | 14 | GIA Req. Rev | 30 | 2 | On Track
P02 | SCADA / Telecom | 21 | 15 | PPA Req. Rev | 34 | 2 | Not Started
P02 | SCADA / Telecom | 22 | 16 | Vendor Sel / Long-Lead Eqp | 38 | 2 | Not Started
P02 | SCADA / Telecom | 23 | 17 | Points List Rev | 44 | 2 | Not Started
P02 | SCADA / Telecom | 24 | 18 | TELCOM / Wless (Order/Install) | 48 | 2 | Not Started
P02 | SCADA / Telecom | 25 | 19 | SCADA FAT | 54 | 2 | Not Started
P02 | SCADA / Telecom | 26 | 20 | Primary Telco | 60 | 2 | Not Started
P02 | HV O&M | 27 | 21 | Initial Design Rev. (ongoing) | 36 | 1 | Not Started
P02 | HV O&M | 28 | 22 | HV Quality Rev. (ongoing) | 42 | 1 | Not Started
P02 | HV O&M | 29 | 23 | MPT Del. / Inst. | 48 | 1 | Not Started
P02 | HV O&M | 30 | 24 | Commissioning (CMX) Testing | 54 | 1 | Not Started
P02 | HV O&M | 31 | 25 | Punch List Items | 58 | 1 | Not Started
P02 | HV O&M | 32 | 26 | CC&C | 62 | 1 | Not Started
P03 | Commercial Analytics | 1 | C1 | Int. Basis / Curt | 5 | 5 | On Track
P03 | Commercial Analytics | 2 | C2 | Ext. Basis / Curt | 16 | 5 | Not Started
P03 | Commercial Analytics | 3 | C3 | Study Refresh | 30 | 5 | Not Started
P03 | Commercial Analytics | 4 | C4 | 3rd Party Study | 38 | 5 | Not Started
P03 | Commercial Analytics | 5 | C5 | Ext. Re-finance | 58 | 5 | Not Started
P03 | Commercial Analytics | 6 | C6 | Outage Monitoring (Basis/Curt.) | 74 | 5 | Not Started
P03 | Interconnection | 7 | I1 | IX App / POI | 5 | 4 | On Track
P03 | Interconnection | 8 | I2 | IX Studies | 16 | 4 | Not Started
P03 | Interconnection | 9 | I3 | GIA Execution | 30 | 4 | Not Started
P03 | Interconnection | 10 | I4 | Dyn Settings (Analysis) | 38 | 4 | Not Started
P03 | Interconnection | 11 | I5 | Dyn Settings (Testing) | 58 | 4 | Not Started
P03 | Interconnection | 12 | I6 | As-Built Mods & LC Release | 74 | 4 | Not Started
P03 | HV Engineering | 13 | 7 | MPT / HV Eqp Long-Lead | 2 | 3 | On Track
P03 | HV Engineering | 14 | 8 | E&P / OTB | 9 | 3 | On Track
P03 | HV Engineering | 15 | 9 | FacStudy / POI-HV Review | 28 | 3 | At Risk
P03 | HV Engineering | 16 | 10 | Reactive & PQ (Studies) | 38 | 3 | Not Started
P03 | HV Engineering | 17 | 11 | PEC | 50 | 3 | Not Started
P03 | HV Engineering | 18 | 12 | V & Q Setting (Testing) | 58 | 3 | Not Started
P03 | HV Engineering | 19 | 13 | As-Built SLD | 72 | 3 | Not Started
P03 | SCADA / Telecom | 20 | 14 | GIA Req. Rev | 30 | 2 | Not Started
P03 | SCADA / Telecom | 21 | 15 | PPA Req. Rev | 34 | 2 | Not Started
P03 | SCADA / Telecom | 22 | 16 | Vendor Sel / Long-Lead Eqp | 38 | 2 | Not Started
P03 | SCADA / Telecom | 23 | 17 | Points List Rev | 44 | 2 | Not Started
P03 | SCADA / Telecom | 24 | 18 | TELCOM / Wless (Order/Install) | 48 | 2 | Not Started
P03 | SCADA / Telecom | 25 | 19 | SCADA FAT | 54 | 2 | Not Started
P03 | SCADA / Telecom | 26 | 20 | Primary Telco | 60 | 2 | Not Started
P03 | HV O&M | 27 | 21 | Initial Design Rev. (ongoing) | 36 | 1 | Not Started
P03 | HV O&M | 28 | 22 | HV Quality Rev. (ongoing) | 42 | 1 | Not Started
P03 | HV O&M | 29 | 23 | MPT Del. / Inst. | 48 | 1 | Not Started
P03 | HV O&M | 30 | 24 | Commissioning (CMX) Testing | 54 | 1 | Not Started
P03 | HV O&M | 31 | 25 | Punch List Items | 58 | 1 | Not Started
P03 | HV O&M | 32 | 26 | CC&C | 62 | 1 | Not Started
P04 | Commercial Analytics | 1 | C1 | Int. Basis / Curt | 5 | 5 | On Track
P04 | Commercial Analytics | 2 | C2 | Ext. Basis / Curt | 16 | 5 | On Track
P04 | Commercial Analytics | 3 | C3 | Study Refresh | 30 | 5 | On Track
P04 | Commercial Analytics | 4 | C4 | 3rd Party Study | 38 | 5 | On Track
P04 | Commercial Analytics | 5 | C5 | Ext. Re-finance | 58 | 5 | Not Started
P04 | Commercial Analytics | 6 | C6 | Outage Monitoring (Basis/Curt.) | 74 | 5 | Not Started
P04 | Interconnection | 7 | I1 | IX App / POI | 5 | 4 | On Track
P04 | Interconnection | 8 | I2 | IX Studies | 16 | 4 | On Track
P04 | Interconnection | 9 | I3 | GIA Execution | 30 | 4 | On Track
P04 | Interconnection | 10 | I4 | Dyn Settings (Analysis) | 38 | 4 | On Track
P04 | Interconnection | 11 | I5 | Dyn Settings (Testing) | 58 | 4 | Not Started
P04 | Interconnection | 12 | I6 | As-Built Mods & LC Release | 74 | 4 | Not Started
P04 | HV Engineering | 13 | 7 | MPT / HV Eqp Long-Lead | 2 | 3 | On Track
P04 | HV Engineering | 14 | 8 | E&P / OTB | 9 | 3 | On Track
P04 | HV Engineering | 15 | 9 | FacStudy / POI-HV Review | 28 | 3 | On Track
P04 | HV Engineering | 16 | 10 | Reactive & PQ (Studies) | 38 | 3 | On Track
P04 | HV Engineering | 17 | 11 | PEC | 50 | 3 | At Risk
P04 | HV Engineering | 18 | 12 | V & Q Setting (Testing) | 58 | 3 | Not Started
P04 | HV Engineering | 19 | 13 | As-Built SLD | 72 | 3 | Not Started
P04 | SCADA / Telecom | 20 | 14 | GIA Req. Rev | 30 | 2 | On Track
P04 | SCADA / Telecom | 21 | 15 | PPA Req. Rev | 34 | 2 | On Track
P04 | SCADA / Telecom | 22 | 16 | Vendor Sel / Long-Lead Eqp | 41 | 2 | Delayed
P04 | SCADA / Telecom | 23 | 17 | Points List Rev | 44 | 2 | Not Started
P04 | SCADA / Telecom | 24 | 18 | TELCOM / Wless (Order/Install) | 48 | 2 | Not Started
P04 | SCADA / Telecom | 25 | 19 | SCADA FAT | 54 | 2 | Not Started
P04 | SCADA / Telecom | 26 | 20 | Primary Telco | 60 | 2 | Not Started
P04 | HV O&M | 27 | 21 | Initial Design Rev. (ongoing) | 36 | 1 | At Risk
P04 | HV O&M | 28 | 22 | HV Quality Rev. (ongoing) | 42 | 1 | Not Started
P04 | HV O&M | 29 | 23 | MPT Del. / Inst. | 51 | 1 | Not Started
P04 | HV O&M | 30 | 24 | Commissioning (CMX) Testing | 54 | 1 | Not Started
P04 | HV O&M | 31 | 25 | Punch List Items | 58 | 1 | Not Started
P04 | HV O&M | 32 | 26 | CC&C | 62 | 1 | Not Started
P05 | Commercial Analytics | 1 | C1 | Int. Basis / Curt | 5 | 5 | On Track
P05 | Commercial Analytics | 2 | C2 | Ext. Basis / Curt | 16 | 5 | On Track
P05 | Commercial Analytics | 3 | C3 | Study Refresh | 30 | 5 | On Track
P05 | Commercial Analytics | 4 | C4 | 3rd Party Study | 38 | 5 | On Track
P05 | Commercial Analytics | 5 | C5 | Ext. Re-finance | 58 | 5 | On Track
P05 | Commercial Analytics | 6 | C6 | Outage Monitoring (Basis/Curt.) | 74 | 5 | Not Started
P05 | Interconnection | 7 | I1 | IX App / POI | 5 | 4 | On Track
P05 | Interconnection | 8 | I2 | IX Studies | 16 | 4 | On Track
P05 | Interconnection | 9 | I3 | GIA Execution | 30 | 4 | On Track
P05 | Interconnection | 10 | I4 | Dyn Settings (Analysis) | 38 | 4 | On Track
P05 | Interconnection | 11 | I5 | Dyn Settings (Testing) | 58 | 4 | On Track
P05 | Interconnection | 12 | I6 | As-Built Mods & LC Release | 74 | 4 | Not Started
P05 | HV Engineering | 13 | 7 | MPT / HV Eqp Long-Lead | 2 | 3 | On Track
P05 | HV Engineering | 14 | 8 | E&P / OTB | 9 | 3 | On Track
P05 | HV Engineering | 15 | 9 | FacStudy / POI-HV Review | 28 | 3 | On Track
P05 | HV Engineering | 16 | 10 | Reactive & PQ (Studies) | 38 | 3 | On Track
P05 | HV Engineering | 17 | 11 | PEC | 50 | 3 | On Track
P05 | HV Engineering | 18 | 12 | V & Q Setting (Testing) | 58 | 3 | On Track
P05 | HV Engineering | 19 | 13 | As-Built SLD | 72 | 3 | Not Started
P05 | SCADA / Telecom | 20 | 14 | GIA Req. Rev | 30 | 2 | On Track
P05 | SCADA / Telecom | 21 | 15 | PPA Req. Rev | 34 | 2 | On Track
P05 | SCADA / Telecom | 22 | 16 | Vendor Sel / Long-Lead Eqp | 38 | 2 | On Track
P05 | SCADA / Telecom | 23 | 17 | Points List Rev | 44 | 2 | On Track
P05 | SCADA / Telecom | 24 | 18 | TELCOM / Wless (Order/Install) | 48 | 2 | On Track
P05 | SCADA / Telecom | 25 | 19 | SCADA FAT | 63 | 2 | Delayed
P05 | SCADA / Telecom | 26 | 20 | Primary Telco | 60 | 2 | At Risk
P05 | HV O&M | 27 | 21 | Initial Design Rev. (ongoing) | 36 | 1 | On Track
P05 | HV O&M | 28 | 22 | HV Quality Rev. (ongoing) | 42 | 1 | On Track
P05 | HV O&M | 29 | 23 | MPT Del. / Inst. | 48 | 1 | On Track
P05 | HV O&M | 30 | 24 | Commissioning (CMX) Testing | 66 | 1 | Delayed
P05 | HV O&M | 31 | 25 | Punch List Items | 58 | 1 | At Risk
P05 | HV O&M | 32 | 26 | CC&C | 62 | 1 | On Track

## KeyActions
ProjectID | Seq | ActionItem | Owner | Due
P00 | 1 | [ Action item / decision needed ] | [ Owner ] | [ Due ]
P00 | 2 | [ Action item / decision needed ] | [ Owner ] | [ Due ]
P00 | 3 | [ Action item / decision needed ] | [ Owner ] | [ Due ]
P00 | 4 | [ Action item / decision needed ] | [ Owner ] | [ Due ]
P00 | 5 | [ Action item / decision needed ] | [ Owner ] | [ Due ]
P01 | 1 | Finalize PEC scope & schedule with Oncor | K. Rivera | 07/15/2026
P01 | 2 | Approve reactive power study addendum | HV Eng | 07/22/2026
P01 | 3 | Confirm SCADA points list freeze | D. Okafor | 08/01/2026
P01 | 4 | Sign off long-lead vendor QA plan | A. Chen | 08/05/2026
P01 | 5 | Refresh curtailment basis for PPA true-up | Comm Analytics | 08/12/2026
P02 | 1 | IX cost overrun mitigation plan with APS | S. Patel | 07/18/2026
P02 | 2 | Re-baseline POI ISD (utility crew availability) | S. Patel | 07/25/2026
P02 | 3 | Decide OTB / E&P execution window | C. Ferraro | 08/08/2026
P02 | 4 | Complete basis / curtailment study refresh | Comm Analytics | 08/15/2026
P02 | 5 | Select PCS vendor — LOI | R. Dominguez | 08/29/2026
P03 | 1 | Execute GIA with PJM / ComEd | E. Kowalski | 08/30/2026
P03 | 2 | Issue EPC RFP | N. Adeyemi | 09/15/2026
P03 | 3 | Convert MPT LOI to PO | H. Yamada | 09/30/2026
P03 | 4 | Kick off reactive & PQ studies | H. Yamada | 10/15/2026
P03 | 5 | Safe-harbor equipment allocation decision | N. Adeyemi | 10/31/2026
P04 | 1 | Expedite plan for 8-week MPT delivery slip | P. Lindqvist | 07/10/2026
P04 | 2 | PEC readiness review with Georgia Power | V. Osei | 07/24/2026
P04 | 3 | Approve revised commissioning sequence | I. Novak | 08/07/2026
P04 | 4 | Close punch on gen-tie ROW restoration | McCarthy | 08/21/2026
P04 | 5 | Confirm breaker upgrade ISD with TO | V. Osei | 08/28/2026
P05 | 1 | SCADA FAT retest — vendor corrective actions | Z. Haddad | 08/01/2026
P05 | 2 | Re-sequence CMX testing to protect COD | Q. Larsen | 08/08/2026
P05 | 3 | Negotiate IX cost true-up with NV Energy | O. Bennett | 08/15/2026
P05 | 4 | Punch list burn-down plan | Q. Larsen | 09/01/2026
P05 | 5 | CC&C documentation package prep | M. Salinas | 09/15/2026